## CAPEX + CONSULTANCY
PROCURING ENTITY NAME: Citizen Entrepreneurial Development Agency
FINANCIAL YEAR: 2023-2024
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
Administration
ADM 001 | Supply and delivery of office furniture | 868000 |  | Open domestic bidding method | Supplies | 868000 | 2023-07-04 | 2023-08-02 | 2023-08-31 | 2023-09-07 | 2023-09-08 | 2023-09-22 | 2023-10-31 | 2023-10-31
ADM 002 | Supply and Delivery of Outdoor Furniture | 121438.22 |  | Request for quotation method | Supplies | 121438.22 | 2023-06-20 | 2023-07-05 | 2023-07-10 | 2023-07-10 | 2023-07-11 | 2023-07-19 | 2023-07-31 | 2023-07-31
ADM 003 | Supply and Delivery of Office Furniture for New Gaborone Branch 1 | 105250 |  | Request for quotation method | Supplies | 105250 | 2023-06-20: Procurement on hold until Branch is located and works are completed
ADM 004 | Supply and Delivery of Office Furniture for New CEDA Tutume Branch | 150250 |  | Request for quotation method | Supplies | 105250 | 2023-06-20: Procurement on hold until Branch is located and works are completed
ADM 005 | Supply, delivery and Installation of Power back up (Solar Power or generator) at CEDA Hukuntsi, Shakawe, Kasane and Letlhakane | 600000 |  | Open domestic bidding method | Works | 600000 | 2023-07-04 | 2023-08-02 | 2023-08-31 | 2023-09-07 | 2023-09-08 | 2023-09-22 | 2023-10-31 | 2023-10-31
ADM 006 | Provision of office works at new CEDA Kanye Branch | 1800000 |  | Open domestic bidding method | Works | 1800000 | 2023-06-20: Procurement on hold as layout is being designed then BOQ will be drafted
ADM 007 | Provision of office works at new CEDA Molepolole Branch | 1524955 |  | Open domestic bidding method | Works | 1524955 | 2023-06-20: Procurement on hold until suitable Branch location is identified for relocation
ADM 008 | Provision of office works at new CEDA Maun Branch | 1500000 |  | Open domestic bidding method | Works | 1500000 | 2023-06-20: Procurement on hold until suitable Branch location is identified for relocation
ADM 009 | Provision of office works at new CEDA Gaborone Branch 1 | 1390000 |  | Open domestic bidding method | Works | 1390000 | 2023-06-20: Procurement on hold until Branches are located and works are completed
ADM 010 | Provision of office works at new CEDA Tutume Branch | 1121600 |  | Open domestic bidding method | Works | 1121600 | 2023-06-20: Procurement on hold until Branches are located and works are completed
ADM 011 | Provision of office works at new CEDA Kasane Branch | 1600000 |  | Open domestic bidding method | Works | 1600000 | 2023-06-20: Procurement on hold until suitable Branch location is identified for relocation
Information Technology
IT 001 | Provision of SAP Success Factor for CEDA | 2100000 |  | Direct Procurement | Services | 2100000 | 2023-07-03 | 2023-07-17 | 2023-07-28 | 2023-07-31 | 2023-08-04 | 2023-08-11 | 2023-11-30 | 2023-11-30
IT 002 | Provision of Access Control Software Upgrade for CEDA | 300000 |  | Request for quotation method | Services | 300000 | 2023-07-03 | 2023-07-19 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-31 | 2023-09-29 | 2023-09-29
IT 003 | Provision of Laws of Botswana CD-ROM (2-4 user licenses) | 150000 |  | Direct Procurement | Services | 150000 | 2023-06-20 | 2023-07-05 | 2023-07-10 | 2023-07-10 | 2023-07-11 | 2023-07-19 | 2023-07-31 | 2023-07-31
IT 004 | Provision of SAP S/4 HANA Upgrade from SAP ECC 6.0 | 10000000 |  | Open international bidding method | Services | 10000000 | 2023-07-03 | 2023-08-15 | 2023-08-30 | 2023-09-01 | 2023-09-05 | 2023-09-19 | 2024-09-18 | 2024-09-19
IT 005 | Provision of Mail Archiving Software for CEDA | 250000 |  | Request for quotation method | Services | 250000 | 2023-06-20 | 2023-07-05 | 2023-07-10 | 2023-07-10 | 2023-07-11 | 2023-07-19 | 2023-07-31 | 2023-07-31
IT 006 | Supply, Delivery and Installation of CCTV at New CEDA Gaborone Branch 1 including support | 500000 |  | Open domestic bidding method | Supplies | 450000 | 2023-06-20: Procurement on hold until Branches are located and works are completed
IT 007 | Supply, Delivery and Installation of CCTV at New CEDA Tutume Branch including support | 500000 |  | Open domestic bidding method | Supplies | 450000 | 2023-06-20: Procurement on hold until Branches are located and works are completed
IT 008 | Supply, Delivery and Installation of new CCTV at New CEDA Molepolole including support and decommissioning | 500000 |  | Open domestic bidding method | Supplies | 450000 | 2023-06-20: Procurement on hold until suitable Branch location is identified for relocation
IT 009 | Provision of a Record Management System for CEDA | 1500000 |  | Open domestic bidding method | Services | 1500000 | 2023-07-04 | 2023-08-02 | 2023-08-31 | 2023-09-07 | 2023-09-11 | 2023-09-25 | 2023-12-14 | 2023-12-14
IT 010 | Supply and delivery of ICT Equipment (Computers, laptops and switch) | 1798102 |  | Open domestic bidding method | Supplies | 1798102 | 2023-07-03 | 2023-08-02 | 2023-08-31 | 2023-09-07 | 2023-09-11 | 2023-09-25 | 2023-10-31 | 2023-10-31
IT 011 | Supply and delivery of Hana Complaint Servers | 3500000 |  | Open domestic bidding method | Supplies | 3500000 | 2023-06-20: Procurement dependent on the award of the tender for SAP S/4 HANA Upgrade from SAP ECC 6.0
IT 012 | Supply and Delivery of Router and Switch for new CEDA Gaborone 1 Branch | 120000 |  | Request for quotation method | Supplies | 120000 | 2023-06-20: Procurement on hold until Branches are located and works are completed
IT 013 | Supply and Delivery of Router and Switch for new CEDA Tutume Branch | 120000 |  | Request for quotation method | Supplies | 120000 | 2023-06-20: Procurement on hold until Branches are located and works are completed
IT 014 | Supply and Delivery of Router and Switch for CEDA new Molepolole Branch | 120000 |  | Request for quotation method | Supplies | 120000 | 2023-06-20: Procurement on hold until suitable Branch location is identified for relocation
IT 015 | Provision of Network Cabling at CEDA new Molepolole Branch | 100000 |  | Request for quotation method | Supplies | 100000 | 2023-06-20: Procurement on hold until suitable Branch location is identified for relocation
IT 016 | Supply, delivery and installation of a New UPS System at CEDA Selebi Phikwe, Hukuntsi and Kasane Branch | 229515 |  | Request for quotation method | Supplies | 229515 | 2023-07-03 | 2023-07-19 | 2023-07-25 | 2023-07-26 | 2023-07-27 | 2023-07-31 | 2023-09-29 | 2023-09-29
IT 017 | Leasing of photocopying machines at CEDA Head Office and its Branches | 674817 |  | Open domestic bidding method | Services | 674817 | 2023-07-03 | 2023-08-02 | 2023-08-31 | 2023-09-07 | 2023-09-11 | 2023-10-01 | 2026-09-03 | 2026-09-03
Consultancy
Con 001 | Architectural Services for New CEDA Gaborone 1 Branch | 150000 |  | Request for quotation method | Services | 150000 | 2023-06-20: Procurement will be done upon completion of the Branch relocation and New Branches respectively.
Con 002 | Architectural Services for New CEDA Tutume Branch | 150000 |  | Request for quotation method | Services | 150000 | 2023-06-20: Procurement will be done upon completion of the Branch relocation and New Branches respectively.
Con 003 | Need Based Consultancy | 150000 |  | Request for quotation method | Services | 150000 | 2023-06-20: Need based consultancy and it does not have a set date due to its nature.
Con 004 | Provision of a Annual Remuneration Survey | 480000 |  | Direct Procurement | Services | 480000 | 2023-05-01 | 2023-05-15 | 2023-05-15 | 2023-05-15 | 2023-05-16 | 2023-05-16 | 2023-05-25 | 2023-05-25
Con 005 | Provision of a Employee Experience Survey | 230000 |  | Request for quotation method | Services | 230000 | 2023-08-01 | 2023-08-14 | 2023-08-17 | 2023-08-18 | 2023-08-21 | 2023-08-25 | 2023-09-27 | 2023-09-27
Con 006 | Provision of a Employee Performance Management System | 376660 |  | Request for quotation method | Services | 376660 | 2023-06-20: Additional funds for operating expense for SAP Success Factor
Con 007 | Provision of a Annual Security assessment and mitigation | 400000 |  | Request for quotation method | Services | 400000 | 2024-01-03 | 2024-01-17 | 2024-01-22 | 2024-01-24 | 2024-01-26 | 2024-01-29 | 2024-02-28 | 2024-02-28
Con 008 | Provision of a Robust Cybersecurity Management | 350000 |  | Request for quotation method | Services | 350000 | 2023-07-03 | 2023-07-17 | 2023-07-21 | 2023-07-23 | 2023-07-25 | 2023-07-26 | 2023-08-25 | 2023-08-25
Con 009 | Provision of a Re-enforce IT governance | 250000 |  | Request for quotation method | Services | 250000 | 2023-07-03 | 2023-07-17 | 2023-07-21 | 2023-07-23 | 2023-07-25 | 2023-07-26 | 2023-08-25 | 2023-08-25
Con 010 | Provision of a Product Development | 298518.32 |  | Request for quotation method | Services | 298518.32 | 2023-05-01 | 2023-05-15 | 2023-05-19 | 2023-05-22 | 2023-05-24 | 2023-05-25 | 2023-05-29 | 2023-05-29
Con 011 | Provision of Resource Mobilisation Benchmarkings | 300000 |  | Request for quotation method | Services | 300000 | 2023-05-01 | 2023-05-15 | 2023-05-19 | 2023-05-22 | 2023-05-24 | 2023-05-25 | 2023-06-29 | 2023-06-29
Con 012 | Review of CEDA Credit Appraisal Models | 2625000 |  | Open domestic bidding method | Services | 2625000 | 2023-07-04 | 2023-08-02 | 2023-08-31 | 2023-09-07 | 2023-09-11 | 2023-09-25 | 2023-12-14 | 2023-12-14
Con 013 | Provision of a Customer Screening Solution | 200000 |  | Request for quotation method | Services | 200000 | 2023-01-25 | 2023-02-23 | 2023-05-26 | 2023-05-31 | 2023-06-06 | 2023-11-01 | 2025-10-30 | 2025-10-30
Con 014 | Provision of a ESG Reporting | 250000 |  | Request for quotation method | Services | 250000 | 2023-06-20 | 2023-07-05 | 2023-07-10 | 2023-07-11 | 2023-07-12 | 2023-07-12 | 2024-03-31 | 2024-03-31
Con 015 | Provision of a Power BI Integration | 283798.33 |  | Request for quotation method | Services | 283798.33 | 2023-05-01 | 2023-05-15 | 2023-05-19 | 2023-05-22 | 2023-05-24 | 2023-05-25 | 2023-09-30 | 2023-09-30