## CAPEX
PROCURING ENTITY NAME: Citizen Entrepreneurial Development Agency
FINANCIAL YEAR: 2023-2024
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
Administration
ADM 001 | Provision of office works at new CEDA Gaborone Branch 1 | 1200000 |  | Open domestic bidding method | Works | 1200000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 002 | Supply and delivery of a vehicle for CEDA Kanye Branch (4x4) | 668220 |  | Restricted Domestic Bidding Method | Supplies | 668220 | 2024-11-18 | 2024-11-22 | 2024-11-27 | 2024-11-29 | 2024-12-02 | 2024-12-02 | 2025-01-31 | 2025-01-31
ADM 003 | Provision of office works at new CEDA Kanye Branch | 2455591 |  | Open domestic bidding method | Works | 2455591 | 2024-04-11 | 2024-04-26 | 2024-07-01 | 2024-07-12 | 2024-07-19 | 2024-08-12 | 2024-11-30 | 2024-11-30
ADM 004 | Pavement of staff houses in Tsabong | 830000 |  | Open domestic bidding method | Works | 830000 | 2024-01-06 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-20 | 2024-01-31 | 2024-01-31
ADM 005 | Purchase of staff houses in Tsabong | 1320000 |  | N/A | Supplies | 1320000 | Staff houses were purchased last year using available savings
ADM 006 | Supply and delivery of a porta cabin for new CEDA Goodhope Branch | 3240000 |  | Open domestic bidding method | Works | 3240000 | Procurement on hold until Branch is located and works are completed
ADM 007 | Provision of office works at new CEDA Maun Branch | 1277000 |  | Open domestic bidding method | Works | 1277000 | Procurement on hold until Branch is located and works are completed
ADM 008 | Supply and delivery of a vehicle for CEDA Kasane Branch (4x4) | 616840 |  | Restricted Domestic Bidding Method | Supplies | 616840 | 2024-11-18 | 2024-11-22 | 2024-11-27 | 2024-11-29 | 2024-12-02 | 2024-12-02 | 2025-01-31 | 2025-01-31
ADM 009 | Provision of office works at new CEDA Kasane Branch | 1042186 |  | Open domestic bidding method | Works | 1042186 | Procurement on hold until Branch is located and works are completed
ADM 010 | Provision of office works at new CEDA Tutume Branch | 1042186 |  | Open domestic bidding method | Works | 1042186 | 2024-07-05 | 2024-08-06 | 2024-10-31 | 2024-11-04 | 2024-11-11 | 2024-12-01 | 2025-07-28 | 2025-07-28
ADM 011 | Supply and delivery of a vehicle for CEDA Selebi Phikwe Branch (4x4) | 503215 |  | Restricted Domestic Bidding Method | Supplies | 503215 | 2024-11-18 | 2024-11-22 | 2024-11-27 | 2024-11-29 | 2024-12-02 | 2024-12-02 | 2025-01-31 | 2025-01-31
ADM 012 | Supply and delivery of a vehicle for CEDA Palapye Branch (Sedan) | 305008 |  | Restricted Domestic Bidding Method | Supplies | 305008 | 2024-11-18 | 2024-11-22 | 2024-11-27 | 2024-11-29 | 2024-12-02 | 2024-12-02 | 2025-01-31 | 2025-01-31
ADM 013 | Purchase of a warehouse | 20000000 |  | Direct Procurement | Supplies | 20000000 | Procurement on hold until siutable warehouse is located and works are completed
Information Technology
ITD 001 | Provision of SAP Success Factor | 2500000 |  | Open International Bidding Method | Services | 2500000 | 2024-11-11 | 2024-12-09 | 2025-01-30 | 2025-02-03 | 2025-02-07 | 2025-02-24 | 2026-02-24 | 2026-02-24
ITD 002 | Provision of SAP S/4 HANA Upgrade | 25000000 |  | Open International Bidding Method | Services | 25000000 | 2024-11-11 | 2024-12-09 | 2025-01-30 | 2025-02-03 | 2025-02-07 | 2025-02-24 | 2026-02-24 | 2026-02-24
ITD 003 | Provision of CEDA Online Phase2 | 1000000 |  | Direct Procurement | Services | 1000000 | 2024-11-11 | 2024-11-22 | 2025-11-25 | 2025-11-27 | 2025-11-29 | 2024-12-02 | 2025-03-31 | 2025-03-31
ITD 004 | Provision of EDRMS Software | 1850000 |  | Open domestic bidding method | Services | 1850000 | Procurement awaiting approval of Policies and Procedures
ITD 005 | Provision of Record Management System | 500000 |  | Open domestic bidding method | Services | 500000 | Procurement awaiting approval of Policies and Procedures
ITD 006 | Supply and delivery of ICT Equipment | 2430000 |  | Open domestic bidding method | Supplies | 2430000 | 2024-11-11 | 2024-12-09 | 2025-01-30 | 2025-02-03 | 2025-02-07 | 2025-02-08 | 2025-03-31 | 2025-03-31

## MACRO PROCURMENT (CAPEX)
Project Code | Project Name | Budget Amount | Activity Name | Procurement Method | Descipline (Supplies/Services / Works) | Estimated Cost | Invitation Date | Tender Close Date | Evaluation completion | Submission for Adjudication | Award Decision | Project Commencement | Project Completion | Activity Report
Administration
ADM 001 | Supply, delivery and installation of CCTV for New Gaborone Branch 1 | 350000 |  | Restricted domestic bidding method | Works | 350000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 002 | Supply, delivery and installation of a fire suppression system for New Gaborone Branch 1 | 100000 |  | Restricted domestic bidding method | Services | 100000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 003 | Supply, delivery and installation of air conditioners for New Gaborone Branch 1 | 200000 |  | Restricted domestic bidding method | Works | 200000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 004 | Provision of network cabling for New Gaborone Branch 1 | 120000 |  | Restricted domestic bidding method | Services | 120000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 005 | Supply and installation of a carport for New Gaborone Branch 1 | 150000 |  | Restricted domestic bidding method | Works | 150000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 006 | Supply and delivery of a filling cabinet for New Gaborone Branch 2 | 126000 |  | Restricted domestic bidding method | Supplies | 126000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 007 | Supply, delivery and installation of CCTV for New Gaborone Branch 2 | 350000 |  | Restricted domestic bidding method | Works | 350000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 008 | Supply, delivery and installation of a fire suppression system for New Gaborone Branch 2 | 100000 |  | Restricted domestic bidding method | Services | 100000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 009 | Supply, delivery and installation of air conditioners for New Gaborone Branch 2 | 200000 |  | Restricted domestic bidding method | Works | 200000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 010 | Provision of network cabling for New Gaborone Branch 1 | 120000 |  | Restricted domestic bidding method | Services | 120000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 011 | Supply, delivery and installation of a back up generator at CEDA Molepolole Branch | 360077 |  | Restricted domestic bidding method | Works | 360077 | 2024-01-06 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-20 | 2024-01-31 | 2024-01-31
ADM 012 | Supply, delivery and installation of a solar power system at Hukuntsi Branch | 450000 |  | Restricted domestic bidding method | Works | 450000 | 2024-11-07 | 2024-11-13 | 2024-11-15 | 2024-11-18 | 2024-11-18 | 2024-11-19 | 2024-11-27 | 2024-11-27
ADM 013 | Supply, delivery and installation of CCTV for New Goodhope Branch | 354560.93 |  | Restricted domestic bidding method | Works | 354560.93 | Procurement on hold until suitable Branch location is identified for relocation
ADM 014 | Supply, delivery and installation of a solar power system at Kasane Branch | 450000 |  | Restricted domestic bidding method | Works | 450000 | Procurement on hold until suitable Branch location is identified for relocation
ADM 015 | Supply, delivery and installation of a solar power system at Shakawe Branch | 450000 |  | Restricted domestic bidding method | Works | 450000 | 2024-01-06 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-20 | 2024-01-31 | 2024-01-31
ADM 016 | Supply, delivery and installation of CCTV for New Tutume Branch | 357778 |  | Restricted domestic bidding method | Works | 357778 | Procurement on hold until Branch is opened and works are completed
ADM 017 | Supply, delivery and installation of a solar power system at new CEDA Tutume Branch | 450000 |  | Restricted domestic bidding method | Works | 450000 | Procurement on hold until Branch is opened and works are completed
ADM 018 | Supply, delivery and installation of a solar power system at Letlhakane Branch | 450000 |  | Restricted domestic bidding method | Works | 450000 | Procurement on hold until Branch is opened and works are completed
ADM 019 | Supply, delivery and installation of a back up generator at CEDA Francistown Branch | 381835 |  | Restricted domestic bidding method | Works | 381835 | 2024-01-06 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-20 | 2024-01-31 | 2024-01-31
ADM 020 | Supply, delivery and installation of air conditioners for Selebi Phikwe Branch | 114490 |  | Restricted domestic bidding method | Works | 114490 | 2024-10-01 | 2024-10-10 | 2024-10-11 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-22 | 2024-10-22
ADM 021 | Supply and delivery of outdoor furniture | 121438 |  | Restricted domestic bidding method | Supplies | 121438 | Procurement awaiting specifications
ADM 022 | Supply and delivery of workstation screens | 100000 |  | Restricted domestic bidding method | Supplies | 100000 | 2024-11-12 | 2024-11-15 | 2024-11-18 | 2024-11-19 | 2024-11-20 | 2024-11-25 | 2024-11-29 | 2024-11-29
Information Technology
ITD 001 | Provision of Rapid 7 Vulnerability Scanner | 275000 |  | Restricted domestic bidding method | Services | 275000 | Procurement was done last financial year using savings
ITD 002 | Provision of Mail Archiving Software | 250000 |  | Restricted domestic bidding method | Services | 250000 | 2024-01-06 | 2024-01-13 | 2024-01-14 | 2024-01-15 | 2024-01-16 | 2024-01-20 | 2024-01-31 | 2024-01-31
ITD 003 | Supply and delivery of CEDA Core Switch & Additional AP's | 160000 |  | Restricted domestic bidding method | Supplies | 160000 | 2024-11-07 | 2024-11-13 | 2024-11-15 | 2024-11-18 | 2024-11-18 | 2024-11-19 | 2024-11-27 | 2024-11-27
ITD 004 | Supply and delivery of CISCO Router and Switch (Tutume and Goodhope) | 310000 |  | Restricted domestic bidding method | Supplies | 310000 | Procurement on hold until Branch is opened and works are completed
ITD 005 | Supply and delivery of UPS (Tutume and Goodhope) | 150000 |  | Restricted domestic bidding method | Supplies | 150000 | Procurement on hold until Branch is opened and works are completed
ITD 006 | Supply and delivery of Fire Suppression (Tutume and Goodhope) | 120000 |  | Restricted domestic bidding method | Supplies | 120000 | Procurement on hold until Branch is opened and works are completed
ITD 007 | Supply and delivery of IPADS | 140000 |  | Direct Procurement | Supplies | 140000 | 2024-10-01 | 2024-10-10 | 2024-10-11 | 2024-10-14 | 2024-10-15 | 2024-10-16 | 2024-10-22 | 2024-10-22
ITD 008 | Supply and delivery of Network Cabling (Tutume and Goodhope) | 450000 |  | Restricted domestic bidding method | Services | 450000 | Procurement on hold until Branch is relocated and works are completed